## Title
This document records, in a slightly more systematic way, the changes introduced at each commit and the intentions for the next commit

## Categories
Category_ID | Description
A | Improvements
B | Hierarchies and Filters
C | Bugs
D | Data
E | Tidying
F | Validation
G | Documentation
H | Collaboration

## Category Detail
Category_ID | Item_ID | Category_Detail_ID | Description
A | 1 | A.1 | Introduce this tracking system
A | 2 | A.2 | Deal with three-digit aggregates
A | 3 | A.3 | Separate scripts
B | 1 | B.1 | Deal with redacted data
B | 2 | B.2 | Create Analysis Server
B | 3 | B.3 | Hierarchy for Date
C | 1 | C.1 | Fix LFS All Provinces
C | 2 | C.2 | Fix Indicator Names
C | 3 | C.3 | Remove blanks
D | 1 | D.1 | Add Monthly all-Canada data to July 2020
D | 2 | D.2 | Annualise the monthly data internally
D | 3 | D.3 | Merge and simplify LFS
D | 4 | D.4 | Create reduced fact file
H | 1 | H.1 | Set up 'Teams' channel for creative datalab
H | 2 | H.2 | Set up website for creative datalab
B | 4 | B.4 | Indicator Hierarchies
C | 4 | C.4 | Auto-generate dimSource
B | 5 | B.5 | New attributes for early-warning NAICS definitions
E | 1 | E.1 | More Informative Names for Creative Categories
H | 3 | H.3 | Integrate CSA categories

## Actions
Action_ID | Category_Detail_ID | Subcategory_ID | Date Entered | Action | Notes
A.1.a | A.1 | a | 2020-12-17 | Set up the data model | The relations in the data model may be wrong due to lack of data. Correct when we have more entries
A.2.a | A.2 | a | 2020-12-20 | Create new attribute in dimIndustry that allows us to distinguish 4-digit from 3 and 2-digit codes
A.3.a | A.3 | a | 2020-12-20 | Separate SQL scripts for the metadata tables and for the data tables and views
B.1.a | B.1 | a | 2020-12-18 | Add a 'redacted' field in FactSource for those NAICS codes that have redacted data
B.2.a | B.2 | a | 2020-12-18 | Create the Analysis Server Project
B.3.a | B.3 | a | 2020-12-18 | Hierarchy for Date
B.4.a | B.4 | a | 2021-03-01 | Create new new CI attributes for 3-digit NAICS
C.1.a | C.1 | a | 2020-12-18 | Scaling
C.2.a | C.2 | a | 2020-12-19 | Change 'Number of Jobs' | In one case says 'Total Number of Jobs' and in other 'Total Jobs'
C.3.a | C.3 | a | 2020-12-19 | Get rid of blank sources
C.3.b | C.3 | b | 2020-12-19 | Get rid of blank indicators
C.3.c | C.3 | c | 2020-12-20 | Remove unused indicators from P&H
D.1.a | D.1 | a | 2020-12-17 | Prepare the data source | Layout needs to be the same as existing which covers only Manitoba and Canada
D.2.a | D.2 | a | 2020-12-17 | Annualise the all-provinces data | Try it out on one case first, then extend to the others
D.3.a | D.3 | a | 2020-12-19 | Merge the monthly all-provinces LFS data
D.3.b | D.3 | b | 2020-12-19 | Replace September Monthly MAN-CAN with November MAN-CAN | Also fix 'Number of Jobs' for this source
D.3.c | D.3 | c | 2021-03-01 | Unified notation for Monthly LFS MAN CAN only
D.4.a | D.4 | a | 2020-12-19 | Create scripts to give dimIndicator and DimSource
D.4.b | D.4 | b | 2021-03-01 | Populate Source Table from Fact File
E.1.a | E.1 | a | 2021-03-04 | Change 'Music' to 'Music and Performing Arts'
H.1.a | H.1 | a | 2020-12-17 | Teams Channel Management
B.4.d | B.1 | d | 2021-03-04 | Hierarchies for the NAICS categories
H.1.b | H.1 | b | 2020-12-20 | Place data in folders in Team and invite participants
H.2.a | H.2 | a | 2020-12-17 | Create website
B.5.a | B.5 | a | 2021-03-05 | Add new attributes for early warnings, proximity, and intensity | Part of the 'early warning' project
D.4.c | D.4 | c | 2021-03-06 | Create an 'LFS only' Query | Part of the 'early warning' project
B.5.b | B.5 | b | 2021-03-20 | Create attributes for Cultural Early Warning and Creative Early Warning | Part of the 'early warning' project
B.5.c | B.5 | c | 2021-03-20 | Corrections to Creative (NESTA) attribute | Part of the 'early warning' project

## Tracking
Action_ID | Date Entered | Commit Date | Status | Commit Title | Tests | Observations | Check ID | Detail | Action
A.1.a | 2020-12-17 | 2020-12-17 | Scrapped | Tracking System | Check the summary | Scrapped in favour of D.1.b | A.1.a | Introduce this tracking system | Set up the data model
A.2.a | 2020-12-20 | 2021-03-04 | Done | Flat Query | New Full Query.xlsx |  | A.2.a | Deal with three-digit aggregates | Create new attribute in dimIndustry that allows us to distinguish 4-digit from 3 and 2-digit codes
A.3.a | 2020-12-20 | 2020-12-20 | Done | Flat Query |  |  | A.3.a | Separate scripts | Separate SQL scripts for the metadata tables and for the data tables and views
B.1.a | 2020-12-18 | 2020-12-18 | Done | Rebase | Test of full monthly with redaction field 18.12.2020 | Scale the data | B.1.a | Deal with redacted data | Add a 'redacted' field in FactSource for those NAICS codes that have redacted data
B.2.a | 2020-12-18 | 18-Dec | Done | Rebase | Test of full monthly with redaction field 18.12.2020 |  | B.2.a | Create Analysis Server | Create the Analysis Server Project
B.3.a | 2020-12-18 | 2021-03-03 | Done |  | New Full Query.xlsx | When the date field is loaded into Power Pivot, it creates a hierarchy automatically | B.3.a | Hierarchy for Date | Hierarchy for Date
B.4.a | 2021-03-01 | 2021-03-04 | Done | Flat Query | New Full Query.xlsx | Instead of attributes, create a new full description query and a new full fact query | B.4.a | Indicator Hierarchies | Create new new CI attributes for 3-digit NAICS
C.1.a | 2020-12-18 | 2020-12-19 | Done | Rebase | Test of full monthly with redaction field 18.12.2020 |  | C.1.a | Fix LFS All Provinces | Scaling
C.2.a | 2020-12-19 | 2020-12-19 | Done | Rebase | Test 201219.xlsx |  | C.2.a | Fix Indicator Names | Change 'Number of Jobs'
C.3.a | 2020-12-19 | 2021-03-04 | Done | Flat Query |  |  | C.3.a | Remove blanks | Get rid of blank sources
C.3.b | 2020-12-19 | 2021-03-04 | Done | Flat Query |  |  | C.3.b | Remove blanks | Get rid of blank indicators
C.3.c | 2020-12-20 | 2020-12-20 | Done | Rebase | Test 201219.xlsx |  | C.3.c | Remove blanks | Remove unused indicators from P&H
D.1.a | 2020-12-17 | 2020-12-17 | Done | Tracking System |  |  | D.1.a | Add Monthly all-Canada data to July 2020 | Prepare the data source
D.2.a | 2020-12-17 | 2020-12-20 | Done | Rebase | Test 201219.xlsx | Power Pivot automatically annualises | D.2.a | Annualise the monthly data internally | Annualise the all-provinces data
D.3.a | 2020-12-19 | 2020-12-19 | Done | Rebase | Test of full monthly with redaction field 18.12.2020 |  | D.3.a | Merge and simplify LFS | Merge the monthly all-provinces LFS data
D.3.b | 2020-12-19 | 2020-12-19 | Done | Rebase | Test of full monthly with redaction field 18.12.2020.xlsx |  | D.3.b | Merge and simplify LFS | Replace September Monthly MAN-CAN with November MAN-CAN
D.3.c | 2021-03-01 | 2021-03-04 | Done | Flat Query | New Full Query.xlsx |  | D.3.c | Merge and simplify LFS | Unified notation for Monthly LFS MAN CAN only
D.4.a | 2020-12-19 | 2020-12-19 | Done | Rebase | Test 201219.xlsx | No gains in size: the data model clearly optimises space usage | D.4.a | Create reduced fact file | Create scripts to give dimIndicator and DimSource
D.4.b | 2021-03-01 | 2021-03-04 | Abandoned | Flat Query |  | Data Model is most efficient storage form so no savings result | D.4.b | Create reduced fact file | Populate Source Table from Fact File
E.1.a | 2021-03-04 | 2021-03-05 | Done | Early Warning First Functioning |  |  | E.1.a | More Informative Names for Creative Categories | Change 'Music' to 'Music and Performing Arts'
H.1.a | 2020-12-17 | 2020-12-18 | Done | N/A | N/A |  | H.1.a | Set up 'Teams' channel for creative datalab | Teams Channel Management
H.1.b | 2020-12-20 | 2021-03-04 | Done | Flat Query |  |  | H.1.b | Set up 'Teams' channel for creative datalab | Place data in folders in Team and invite participants
H.2.a | 2020-12-17 |  | TODO |  |  |  | H.2.a | Set up website for creative datalab | Create website
B.5.a | 2021-03-05 | 2021-03-05 | Done | Early Warning First Functioning | New Full Query.xlsx |  | B.5.a | New attributes for early-warning NAICS definitions | Add new attributes for early warnings, proximity, and intensity
B.4.d | 2021-03-04 | 2021-03-05 | Done | Early Warning First Functioning | New Full Query.xlsx | Can be done with the full query | B.4.d | Indicator Hierarchies | Hierarchies for the NAICS categories
D.4.c | 2021-03-06 | 2021-03-24 | Done | Dataset for Early Warning Paper | New Full Query.xlsx |  | D.4.c | Create reduced fact file | Create an 'LFS only' Query
B.5.b | 2021-03-20 | 2021-03-24 | Done | Dataset for Early Warning Paper | Most spreadsheets in the COVID folder |  | B.5.b | New attributes for early-warning NAICS definitions | Create attributes for Cultural Early Warning and Creative Early Warning
Formulas:
Date Entered = VLOOKUP([Action_ID],Actions!$A2:E36,4,FALSE)

## Other
Outline unstructured plans