## Title
This document records, in a slightly more systematic way, the changes introduced at each commit and the intentions for the next commit

## Categories
Category_ID | Description
A | Improvements
B | Hierarchies and Filters
C | Bugs
D | Data
E | Tidying
F | Validation
G | Documentation
H | Collaboration

## Category Detail
Category_ID | Item_ID | Category_Detail_ID | Description
D | 1 | D.1 | Add Monthly all-Canada data to July 2020
A | 1 | A.1 | Introduce this tracking system
B | 1 | B.1 | Deal with redacted data
H | 1 | H.1 | Set up 'Teams' channel for creative datalab
H | 2 | H.2 | Set up website for creative datalab
D | 2 | D.2 | Annualise the monthly data internally
B | 2 | B.2 | Create Analysis Server
C | 1 | C.1 | Fix LFS All Provinces
B | 3 | B.3 | Hierarchy for Date
C | 2 | C.2 | Fix Indicator Names
D | 3 | D.3 | Merge and simplify LFS
D | 4 | D.4 | Create reduced fact file
C | 3 | C.3 | Remove blanks
A | 2 | A.2 | Deal with three-digit aggregates

## Actions
Action_ID | Category_Detail_ID | Subcategory_ID | Date Entered | Action | Notes
D.1.a | D.1 | a | 2020-12-17 | Prepare the data source | Layout needs to be the same as existing which covers only Manitoba and Canada
A.1.a | A.1 | a | 2020-12-17 | Set up the data model | The relations in the data model may be wrong due to lack of data. Correct when we have more entries
B.1.a | B.1 | a | 2020-12-18 | Add a 'redacted' field in FactSource for those NAICS codes that have redacted data
H.1.a | H.1 | a | 2020-12-17 | Create channel
H.2.a | H.2 | a | 2020-12-17 | Create website
D.2.a | D.2 | a | 2020-12-17 | Annualise the all-provinces data | Try it out on one case first, then extend to the others
B.2.a | B.2 | a | 2020-12-18 | Create the Analysis Server Project
C.1.a | C.1 | a | 2020-12-18 | Scaling
B.3.a | B.3 | a | 2020-12-18 | Hierarchy for Date
C.2.a | C.2 | a | 2020-12-19 | Change 'Number of Jobs' | In one case says 'Total Number of Jobs' and in other 'Total Jobs'
D.3.a | D.3 | a | 2020-12-19 | Merge the monthly all-provinces LFS data
D.3.b | D.3 | b | 2020-12-19 | Replace September Monthly MAN-CAN with November MAN-CAN | Also fix 'Number of Jobs' for this source
D.4.a | D.4 | a | 2020-12-19 | Create scripts to give dimIndicator and DimSource
C.3.a | C.3 | a | 2020-12-19 | Get rid of blank sources
C.3.b | C.3 | b | 2020-12-19 | Get rid of blank indicators
H.1.b | H.1 | b | 2020-12-20 | Place data in folders in Team and invite participants
C.3.c | C.3 | c | 2020-12-20 | Remove unused indicators from P&H
A.2.a | A.2 | a | 2020-12-20 | Create new attribute in dimIndustry that allows us to distinguish 4-digit from 3 and 2-digit codes

## Tracking
Action_ID | Date Entered | Date | Status | Commit Title | Tests | Observations | Check ID | Detail | Action
A.1.a | 2020-12-17 | 2020-12-17 | Scrapped | Tracking System | Check the summary | Scrapped in favour of D.1.b | A.1.a | Introduce this tracking system | Set up the data model
B.1.a | 2020-12-18 | 2020-12-18 | Done | Import LFS All Provinces | Test of full monthly with redaction field 18.12.2020 | Scale the data | B.1.a | Deal with redacted data | Add a 'redacted' field in FactSource for those NAICS codes that have redacted data
B.2.a | 2020-12-18 | 18-Dec | Done | Import LFS All Provinces | Test of full monthly with redaction field 18.12.2020 |  | B.2.a | Create Analysis Server | Create the Analysis Server Project
B.3.a | 2020-12-18 | 18-Dec | TODO |  |  |  | B.3.a | Hierarchy for Date | Hierarchy for Date
C.1.a | 2020-12-18 | 2020-12-19 | Done | Minor Fixes | Test of full monthly with redaction field 18.12.2020 |  | C.1.a | Fix LFS All Provinces | Scaling
C.2.a | 2020-12-19 | 2020-12-19 | Done | Blank Elimination | Test 201219.xlsx |  | C.2.a | Fix Indicator Names | Change 'Number of Jobs'
D.1.a | 2020-12-17 | 2020-12-17 | Done | Tracking System |  |  | D.1.a | Add Monthly all-Canada data to July 2020 | Prepare the data source
D.2.a | 2020-12-17 | 2020-12-20 | Done | Blank Elimination | Test 201219.xlsx | Power Pivot automatically annualises | D.2.a | Annualise the monthly data internally | Annualise the all-provinces data
H.1.a | 2020-12-17 | 2020-12-18 | Done | N/A | N/A |  | H.1.a | Set up 'Teams' channel for creative datalab | Create channel
D.3.a | 2020-12-19 | 2020-12-19 | Done | Minor Fixes | Test of full monthly with redaction field 18.12.2020 |  | D.3.a | Merge and simplify LFS | Merge the monthly all-provinces LFS data
H.2.a | 2020-12-17 |  | TODO |  |  |  | H.2.a | Set up website for creative datalab | Create website
D.3.b | 2020-12-19 | 2020-12-19 | Done | Minor Fixes | Test of full monthly with redaction field 18.12.2020.xlsx |  | D.3.b | Merge and simplify LFS | Replace September Monthly MAN-CAN with November MAN-CAN
D.4.a | 2020-12-19 | 2020-12-19 | Done | Blank Elimination | Test 201219.xlsx | No gains in size: the data model clearly optimises space usage | D.4.a | Create reduced fact file | Create scripts to give dimIndicator and DimSource
C.3.a | 2020-12-19 |  | TODO |  |  |  | C.3.a | Remove blanks | Get rid of blank sources
C.3.b | 2020-12-19 |  | TODO |  |  |  | C.3.b | Remove blanks | Get rid of blank indicators
H.1.b | 2020-12-20 |  | TODO |  |  |  | H.1.b | Set up 'Teams' channel for creative datalab | Place data in folders in Team and invite participants
C.3.c | 2020-12-20 | 2020-12-20 | Done | Blank Elimination | Test 201219.xlsx |  | C.3.c | Remove blanks | Remove unused indicators from P&H
A.2.a | 2020-12-20 |  | TODO |  |  |  | A.2.a | Deal with three-digit aggregates | Create new attribute in dimIndustry that allows us to distinguish 4-digit from 3 and 2-digit codes
Formulas:
Date Entered = VLOOKUP([Action_ID],Actions!$A2:E27,4,FALSE)

## Other
Outline unstructured plans